DETAILED PROJECT REPORT (DPR)

KEONJHAR DISTRICT INTEGRATED SKILL DEVELOPMENT,
EMPLOYMENT & ENTREPRENEURSHIP MISSION

GOVERNMENT + DMF + CSR + INDUSTRY CONVERGENCE PROJECT

District: Keonjhar (Kendujhar), Odisha
Project Period: 5 Years
Draft for Government, DMF, CSR and Industry Consideration

# 1. Executive Summary

This DPR proposes a five-year, ₹100 crore integrated skill development, employment and entrepreneurship mission for Keonjhar district. The project is designed as a convergence programme rather than a single-scheme proposal, bringing together District Mineral Foundation (DMF), Odisha Government skill-development programmes, CSR, central/state livelihood and apprenticeship programmes, and industry participation.

The proposal prioritises mining-affected communities, rural and tribal youth, women, unemployed and under-employed persons, and young people seeking industry-linked careers. It combines modern training infrastructure with mobilisation, counselling, certification, apprenticeship, placement, entrepreneurship and post-placement support.

Current official sources support the convergence approach. Keonjhar DMF identifies skill development and livelihood as permissible priority areas and states that convergence of budgetary and extra-budgetary resources is required for effective development. The Odisha CSR portal recognises education and skill development, employment-enhancing vocational skills and livelihood enhancement as CSR categories. Odisha also approved Phase II of the Odisha Skill Development Project (OSDP) in January 2026.

# 2. Project at a Glance

| Parameter | Proposed Details |
| --- | --- |
| Project | Keonjhar District Integrated Skill Development, Employment & Entrepreneurship Mission |
| District | Keonjhar (Kendujhar), Odisha |
| Project Period | 5 years |
| Total Indicative Outlay | ₹100 crore |
| Funding Approach | DMF + Odisha Government + CSR + Central/State schemes + Industry |
| Primary Beneficiaries | Rural/tribal youth, mining-affected communities, women, unemployed/under-employed persons |
| Core Outcomes | Training, certification, apprenticeship, placement, self-employment and enterprise creation |
| Implementation | District-led convergence with competent departments, empanelled training partners and industry |
| Geographic Approach | District-wide, with priority to mining-affected and underserved blocks |

# 3. Rationale and Need

Keonjhar has a substantial mining and industrial ecosystem as well as rural and tribal communities whose employability and livelihood opportunities can be strengthened through demand-led skilling. The project therefore proposes an integrated model linking local skills to mining services, engineering, manufacturing, construction, logistics, textiles, healthcare, hospitality, digital services and emerging technologies.

The Keonjhar DMF website reports six skill-development projects with an allocation of ₹8.19 crore and identifies skill development and livelihood as priority areas. The Odisha DMF rules also expressly cover training, training kits, skill-development centres, incubation centres, self-employment schemes, SHG support and forward/backward linkages under skill development and livelihood generation.

# 4. Objectives

- Create a district-wide, industry-linked skill ecosystem.

- Prioritise mining-affected, rural, tribal and economically vulnerable communities.

- Upgrade training capacity in advanced manufacturing, automation, electrical, mechanical, construction and digital skills.

- Create pathways from mobilisation and training to apprenticeship and employment.

- Expand women's participation through dedicated training, enterprise and livelihood support.

- Support self-employment, SHGs, micro-enterprises and local value chains.

- Use convergence to avoid duplication and maximise public and CSR resources.

- Establish measurable monitoring, placement and impact-assessment systems.

# 5. Proposed Programme Components

| Component | Amount (₹ Cr) | Indicative Activities |
| --- | --- | --- |
| District Skill Development Centres | 18 | Centre upgrades, classrooms, labs, equipment and district training network |
| Advanced Mining & Industrial Skills Academy | 12 | Mechanical, electrical, welding, fabrication, maintenance, safety and industrial skills |
| IT/AI/Digital & Industry 4.0 Centre | 8 | Automation, PLC/SCADA, CNC, mechatronics, IoT, digital skills and data-support skills |
| Women Skill & Entrepreneurship Centres | 8 | Women-focused vocational training, enterprise support and market linkage |
| Rural/Tribal Skill & Livelihood Centres | 10 | Block-level training, livelihood skills, local crafts and enterprise support |
| Textile/Apparel/Garment Skills | 7 | Garment, tailoring, production, quality and textile-linked skills |
| Construction/Electrical/Infrastructure Skills | 6 | Electrician, plumbing, masonry, fabrication, construction equipment and related trades |
| Healthcare/Hospitality/Service Skills | 5 | Healthcare support, hospitality, retail, logistics and service-sector skills |
| Apprenticeship & Industry Placement | 7 | Industry MoUs, OJT, apprenticeships, placement drives and post-placement support |
| Entrepreneurship & Startup Incubation | 5 | Business mentoring, incubation, SHG/FPO linkages and enterprise support |
| Mobile Skill Training Units | 4 | Outreach to remote/underserved communities |
| Scholarships/Counselling/Mobilisation | 3 | Career counselling, mobilisation, assessments and inclusion support |
| Digital Learning Platform | 2 | LMS, digital content, candidate tracking and employer interface |
| PMU/Monitoring/Impact Assessment | 3 | Project management, MIS, audits, third-party evaluation |
| TOTAL | 100 |  |

# 6. Indicative Funding & Scheme Convergence

| Funding Source / Scheme | Indicative Envelope (₹ Cr) | Role in DPR | Status / Note |
| --- | --- | --- | --- |
| DMF – Keonjhar | 30 | Mining-affected skill, livelihood, centres, training, enterprise and convergence | To be placed before competent DMF authorities; subject to DMF plan, eligibility and sanction |
| Odisha Government / OSDP-II convergence | 20 | State skill infrastructure, advanced skills, institutional convergence | OSDP Phase II approved by Odisha Cabinet in Jan 2026; component eligibility to be confirmed |
| Corporate CSR | 30 | Centres, equipment, women/youth programmes, digital, apprenticeship and placement | CSR subject to company board/committee approval and Schedule VII eligibility |
| Central/State skill & apprenticeship schemes | 10 | Eligible training, rural skilling and apprenticeship components | Scheme-wise eligibility and current funding ceilings to be validated before sanction |
| Industry contribution | 5 | Equipment, trainers, OJT, apprenticeship, curriculum and placement support | Based on MoUs and industry participation |
| Other convergence / institutional contribution | 5 | Land, facilities, existing assets and complementary programmes | Subject to department/district arrangements |
| TOTAL | 100 |  | Indicative financing architecture; not a sanctioned allocation |

# 7. Immediate Scheme/Convergence Windows

DMF Keonjhar: The official Keonjhar DMF page identifies skill development and livelihood as priority areas. The Odisha DMF rules include training, training kits, skill-development centres, incubation centres, self-employment, SHGs and forward/backward linkages.

OSDP Phase II: Odisha Cabinet approved the second phase of the Odisha Skill Development Project in January 2026. The DPR should seek convergence with eligible OSDP-II components.

Odisha CSR Portal / Schedule VII: Education and Skill Development covers employment-enhancing vocational skills and livelihood enhancement projects. The Odisha CSR portal also allows projects to be listed for corporate consideration.

DDU-GKY / ORMAS: DDU-GKY is a placement-linked skill development programme implemented in Odisha by ORMAS for rural poor youth. Eligible rural youth components should be routed through the applicable ORMAS/DDU-GKY process.

Apprenticeship: Industry-linked apprenticeship/OJT should be integrated into training packages wherever eligible, with employer commitments documented through MoUs.

Other Skill India / State programmes: Eligible courses may be converged with current central/state skilling programmes subject to the applicable guidelines, accreditation, empanelment and funding conditions.

# 8. Target Beneficiaries & Proposed 5-Year Outputs

| Indicator | Proposed Target |
| --- | --- |
| Youth trained | 50,000+ |
| Employment / apprenticeship opportunities | 30,000+ |
| Women beneficiaries | 10,000+ |
| Rural/tribal beneficiaries | 10,000+ |
| Entrepreneurship / self-employment beneficiaries | 5,000+ |
| Industry/Employer MoUs | 50+ |
| Training centres / hubs supported | District + block/cluster network |
| Mobile training units | Multiple units based on access and demand |
| Impact evaluation | Baseline, annual review and end-line assessment |

Targets are planning assumptions for DPR purposes and must be validated through baseline, district skill-gap and market-demand assessments before final sanction.

# 9. Priority Skill Sectors

- Mining services, heavy equipment maintenance and industrial safety

- Mechanical, electrical, welding, fabrication and CNC machining

- Automation, PLC/SCADA, mechatronics, robotics and Industry 4.0

- EV technology, solar/renewable-energy installation and maintenance

- Construction, electrical, plumbing and infrastructure trades

- Textile, apparel, tailoring, garment production and quality

- Healthcare support and allied services

- Hospitality, retail, logistics and customer-service occupations

- IT, digital services, data-support and entrepreneurship

- Food processing, agriculture-linked enterprises, crafts and local livelihoods

# 10. Implementation Structure

| Level | Proposed Responsibility |
| --- | --- |
| District Steering Committee | Policy direction, convergence and inter-department coordination |
| District Administration / Nodal Authority | Project coordination, approvals, monitoring and reporting |
| DMF | Eligible mining-affected components and financing through approved mechanisms |
| Skill Development Department / OSDA or competent authority | Technical convergence, standards and eligible state programmes |
| ORMAS / Rural Development agencies | Eligible rural youth and livelihood components |
| CSR Council / CSR Portal | Project visibility, corporate engagement and convergence facilitation |
| Industry Advisory Group | Demand mapping, curriculum, trainers, OJT and placements |
| PMU | Procurement support, MIS, dashboards, monitoring, documentation and impact evaluation |
| Training Partners | Mobilisation, training, assessment, certification and placement support |

# 11. Five-Year Implementation Roadmap

| Year | Major Activities |
| --- | --- |
| Year 1 | Baseline and skill-gap study; DPR approval; institutional setup; site selection; procurement; pilot training; industry MoUs |
| Year 2 | Centre upgrades; advanced labs; large-scale mobilisation; training and apprenticeship rollout |
| Year 3 | Scale-up across blocks; women/rural/tribal programmes; enterprise incubation; employer expansion |
| Year 4 | Advanced skills; stronger placement network; outcome-based funding; mid-term evaluation and course redesign |
| Year 5 | Consolidation; end-line evaluation; sustainability plan; transfer/continuation of successful components |

# 12. Monitoring, Evaluation & KPIs

- Candidate mobilisation and enrolment

- Attendance and course completion

- Assessment/certification rate

- Apprenticeship/OJT conversion

- Placement rate and retention at 3/6/12 months

- Median/average income improvement where measurable

- Women and vulnerable-group participation

- Enterprise creation and survival

- Employer satisfaction

- Cost per trainee and cost per placement

- Asset utilisation and training-centre occupancy

- Independent annual financial and outcome review

# 13. Sustainability Strategy

After the initial five-year investment, centres should progressively move toward a blended operating model involving government programme convergence, industry-sponsored labs, CSR support, fee-based training where appropriate, apprenticeship-linked employer contributions and enterprise incubation revenue. Public-interest beneficiaries should continue to receive support through eligible government and CSR programmes.

# 14. Risk Management

| Risk | Mitigation |
| --- | --- |
| Training not aligned with jobs | Quarterly employer demand review and curriculum revision |
| Low mobilisation | Panchayat/SHG/community mobilisation and career counselling |
| Dropouts | Counselling, attendance tracking and beneficiary support |
| Weak placements | Pre-signed employer MoUs, apprenticeship and placement cells |
| Duplication of schemes | Single district MIS and scheme-mapping matrix |
| Under-utilised infrastructure | Multi-shift and multi-programme centre utilisation |
| Funding delays | Phased implementation and separate financing packages |
| Quality variation | Accredited/approved partners, standardised SOPs and third-party evaluation |

# 15. Procurement & Financial Management

All expenditure shall follow the procurement, financial, CSR and scheme-specific rules applicable to the funding source. Assets financed through DMF, government or CSR shall be appropriately recorded, tagged and maintained. Component-wise utilisation certificates, physical progress reports, outcome reports and audit documentation shall be maintained.

# 16. Approval & Financing Roadmap

- Conduct district baseline and skill-gap/market-demand assessment.

- Map each DPR component to the relevant DMF, state, central, CSR or industry funding rule.

- Prepare block-wise beneficiary and infrastructure plan.

- Obtain in-principle consideration from the competent district authorities.

- Place eligible DMF components before the appropriate DMF governance mechanism.

- List suitable projects/components through the Odisha CSR platform for corporate consideration.

- Initiate OSDP-II and other state-scheme convergence discussions with the competent department.

- Engage ORMAS/other competent agencies for eligible rural and placement-linked components.

- Sign industry MoUs covering curriculum, equipment, OJT/apprenticeship and placements.

- Release funds and implement in phases subject to sanctions and approved annual action plans.

# 17. Annexure A – Indicative CSR Package Structure

| Package | Indicative Value | Potential CSR Use |
| --- | --- | --- |
| Centre of Excellence | ₹5 Cr | Advanced lab, equipment, trainers and industry-linked courses |
| Women Skill & Enterprise Hub | ₹3 Cr | Training, incubation, market linkage and digital support |
| Rural Mobile Skill Unit | ₹1 Cr | Remote-area training and mobilisation |
| Digital Skill Centre | ₹2 Cr | AI/digital/IT/Industry 4.0 lab |
| Apprenticeship & Placement Fund | ₹3 Cr | Employer engagement, OJT and placement support |
| Scholarship & Inclusion Package | ₹1 Cr | Vulnerable youth/women support |
| Enterprise Incubation Package | ₹2 Cr | Mentoring, tools, market linkage and enterprise support |

# 18. Annexure B – Key Official Reference Points

- Government of Odisha, Chief Minister's Office: Cabinet approval of Phase II of the Odisha Skill Development Project, 10 January 2026.

- Government of Odisha, DMF Keonjhar: district DMF priorities, skill development/livelihood and convergence.

- Government of Odisha, Odisha DMF Rules 2024: skill development and livelihood generation provisions.

- Government of Odisha, CSR Portal: Schedule VII categories and CSR project/convergence platform.

- ORMAS / Government of Odisha: DDU-GKY placement-linked skill development programme.

DRAFT FOR DISCUSSION AND CONVERGENCE — NOT A SANCTION ORDER